## Sheet2
ECN/PCN No | ECN Title / Description | Dept | Year | Approval Pending | Change Required | Details of changes required(Before) | Details of changes required(After) | Reason for Change | Affected Area / Equipment | Document Ref | Requested By | Date Raised | Priority | Risk | Feasibility | Status | Approved By ME/Program Head | Approved By Quality Head | Approved By R&D Head | Approved By Plant Head | Approved By Operations/Maintenance Head | Approved by Purchase Head] | Implementation Owner | Target Date | Delay Status | Days Remaining | Actual Closure Date | Validation Required (Y/N) | Validation Status | Monitoring | Monitoring | Monitoring | ECN Status | Open Points | Open Points-Team
ECN/2026/001 | CA - 88 Cathode New Recipe | Process | 2026 | None | Recipe Change | Conductive carbon % is 1.38 % and binder is 1% | Conductive carbon % is 1.8 % and binder is 0.9% | Reduce resistance + Life cycle Improvement | Cathode Mixing and Calendering | ECR-CA88 | ME Dept | 2026-02-25 | High | Under review | Under review | Raised | — | — | — | — | — | — | ME - Team | 2026-05-31 | On Track | 19 | — | Yes | — | — | — | — | Open | Under review | R&D
ECN/2026/002 | 1.45 g/cc Anode Density electrode | Process | 2026 | All | Process | Anode Electrode Density-1.58 g/cc | Anode Electrode Density-1.45 g/cc | Life cycle and C rate improvement | Anode Calendering Area | ECR-1.45 g/cc | ME Dept | 2026-02-25 | High | Under review | Under review | Raised | — | — | — | — | — | — | ME - Team | 2026-05-31 | Delayed | 19 | — | Yes | — | — | — | — | Open | Risks associated with low peel strength, JR OD rejections and pressure NGs in can insertion discussed along with the action plan addressing these issues. | R&D & ME
ECN/2026/003 | Trim Recycling - Cathode Bottom Trim | Process | 2026 | Bala/Rajesh | New process Implementation | NA | Powder mixed with % trim loss | Improve the yield and waste by reusing material | Cathode Mixing and Calendering | ECR-Cathode Bottom Trim Loss | ME Dept | 2026-05-11 | High | Contamination | Under review | Raised | No | No | No | No | No | No | ME - Team | 2026-05-31 | On Track | 19 | — | Yes | — | — | — | — | Open | Cells to be used for BESS | ME
ECN/2026/004 | Trim Recycling - Anode Bottom Trim | Process | 2026 | None | New process Implementation | NA | Powder mixed with % trim loss | Improve the yield and waste by reusing material | Anode Mixing and Calendering | - | ME Dept | 2026-04-06 | High | Contamination | Under review | Upcoming | — | — | — | — | — | — | ME - Team | 2026-08-31 | On Track | 42 | — | Yes | — | — | — | — | Open | Contamination | ME
ECN/2026/005 | Trim Recycling - Cathode Top Trim | Process | 2026 | None | New process Implementation | NA | Powder mixed with % trim loss | Improve the yield and waste by reusing material | Cathode Mixing and Calendering | - | ME Dept | 2026-04-06 | High | Contamination | Under review | Upcoming | — | — | — | — | — | — | ME - Team | 2026-08-31 | On Track | 42 | — | Yes | — | — | — | — | Open | Vendor Trials Done, equipment to be decided based on the results | ME
ECN/2026/006 | Trim Recycling - Anode Top Trim | Process | 2026 | None | New process Implementation | NA | Powder mixed with % trim loss | Improve the yield and waste by reusing material | Anode Mixing and Calendering | - | ME Dept | 2026-04-06 | High | Contamination | Under review | Upcoming | — | — | — | — | — | — | ME - Team | 2026-08-31 | On Track | 42 | — | Yes | — | — | — | — | Open | Vendor Trials Done, equipment to be decided based on the results | ME
ECN/2026/007 | Auto Dosing In calendering ( Dosing Tower ) | Process + design | 2026 | None | Design Change | Manual | Automated | Reduce the spillage of powder and Increase the tool Speed | Cathode + Anode Calendering Area | - | ME Dept | - | - | - | - | Upcoming | — | — | — | — | — | — | ME - Team | 2026-08-31 | On Track | 42 | — | — | — | — | — | — | — | — | ME
ECN/2026/008 | Auto turret In calendering | Process + design | 2026 | None | Machine Change | Manual | Automated | Reduce the waste of foil + electrode and Setup loss during the start and end of the calendering machine | Cathode + Anode Calendering Area | - | ME Dept | - | - | - | - | Upcoming | — | — | — | — | — | — | ME - Team | — | On Track | - | — | — | — | — | — | — | — | — | ME
ECN/2026/009 | Rev 4 Pin less head - Tab Flattening | Process + design | 2026 | None | Tool Change |  |  | To improve the process yield | Assembly - A | - | ME Dept | - | - | - | - | Upcoming | — | — | — | — | — | — | ME - Team | — | On Track | - | — | — | — | — | — | — | — | — | No open points
ECN/2026/010 | Automated Core Tube Insertion | Process + design | 2026 | None | Machine Change | Manual | Automated | To improve the throughput of the process | Assembly -A | - | ME Dept | - | - | - | - | Upcoming | — | — | — | — | — | — | ME - Team | — | On Track | - | — | — | — | — | — | — | — | — | No open points
ECN/2026/011 | EPR Registeration- QR Compliance | Design | 2026 | Approval Done | QR Code Change | QR without EPR no. | QR with EPR no. | Include EPR no in the QR for the compliance | Assembly -A | EPR number | ME Dept | 2026-03-14 | High | No risk | Usable | Done | No | Yes | Yes | Yes | Yes | Yes | ME - Team | 2026-03-31 | - | - | — | No | — | — | — | — | Done | — | No open points
ECN/2026/012 | Anode and Cathode Slitted Foils | Design | 2026 | Approval Done | Incoming slitted foil-308 mm width in anode and 304 mm in cathode | 340 mm foil width in cathode, 344 mm foil width in anode | 304 mm foil width in cathode, 308 mm foil width in anode | Improve the throughput of the plant by reducing one slitting process | Cathode + Anode Calendering Area | ECR-New Foil | ME Dept | 2026-04-04 | High | No risk | Usable | Done | Yes | Yes | Yes | Yes | Yes | Yes | ME - Team | 2026-03-31 | - | - | — | Yes | — | — | — | — | Done | — | No open points
ECN/2026/013 | Formation Protocol Change-SOC Reduction to 30 % instead of 10% | Design | 2026 | Approval Done | Protocol Change | 10% SOC reduction | 30% SOC reduction | Increasing the throughput of the plant, as there is no risk with the transportation with 30% SOC | Formation | ECR-SOC Reduction | ME Dept | 2026-04-16 | High | No risk | Usable | Done | No | Yes | Yes | Yes | Yes | Yes | ME - Team | 2026-04-30 | - | - | — | No | — | — | — | — | Done | — | No open points
ECN/2026/014 | JR OD upper spec revision to 44.55 mm from 44.4 mm | Design | 2026 | Approval Done | Specification Change | Upper Spec of Average OD:44.4 mm | Upper Spec of Average OD:44.55 mm | To improve the yield of the winding process and to accomodate the electrodes with the higher thickness within the specifications. | Winding | ECR-JR OD rejections | ME Dept | 2026-05-04 | High | No risk | Usable | Done | No | Yes | Yes | Yes | Yes | Yes | ME - Team | 2026-05-10 | - | - | — | Yes | — | — | — | — | ECR Approval Complete | — | No open points
PCN/2026/001 | Semi Automated UV Curing | Process + design | 2026 | Approval Done | Machine Change | Manual | Manual | To improve the throughput of the UV curing process | Assembly -B | PCR-UV Curing | ME Dept | 2026-02-27 | High | No risk | Usable | Done | Yes | Yes | Yes | Yes | Yes | Yes | ME - Team | 2026-05-10 | - | - | — | Yes | — | — | — | — | Done | — | No open points
ECN/2025/001 | Closing Pin weld dimension change in drawing | Design | 2025 | Approval Done | Drawing change | NA | NA | Based on the machine weld capability and product performance the weld dimension are arrived and same need to be update in the drawing | Assembly -B | ECR | ME Dept | 2025-04-01 | High | No | implemented in line | Approved | Yes | Yes | Yes | Yes | Yes | Yes | ME - Team | 2026-03-10 | - | - | — | Yes | — | — | — | — | ECR Approval Complete | — | —
ECN/2025/002 | Change in weld dimensions of Cathode disc welding | Design | 2025 | Approval Done | Drawing change | Weld length: 9 ±0.5 mm Weld width 0.6 ±0.2 mm | Weld length: 7 ±0.5 mm Weld width 1.9 ±0.2 mm | To reduce resultant weld penetration and prevent separator burn issue. | Assembly -A | ECR | ME Dept | 2025-04-01 | High | No | implemented in line | Approved | Yes | Yes | Yes | Yes | Yes | Yes | ME - Team | 2026-03-12 | - | - | — | Yes | — | — | — | — | ECR Approval Complete | — | —
ECN/2025/003 | Change in weld dimensions of Anode disc welding | Design | 2025 | Approval Done | Drawing change | Weld length: 6 ±0.5 mm Weld width 0.6 ±0.2 mm | Weld length: 5 ±0.5 mm Weld width 1.45 ±0.2 mm | To reduce resultant weld penetration and prevent separator burn issue. | Assembly -A | ECR | ME Dept | 2025-04-01 | High | No | implemented in line | Approved | Yes | Yes | Yes | Yes | Yes | Yes | ME - Team | 2026-03-12 | - | - | — | Yes | — | — | — | — | ECR Approval Complete | — | —
ECN/2025/004 | Change in dimensions of Cathode taping | Design | 2025 | Approval Done | Drawing change | Tape top width : 5.2 +/- 1 mm Tape side width : 4.8 +/- 1 mm | Tape top width : 5.2 +/- 3 mm Tape side width : 4.8 +/- 2 mm . | Taping process is currently unable to maintain the tape width on top and side | Assembly -A | ECR | ME Dept | 2025-04-01 | High | No | implemented in line | Approved | Yes | Yes | Yes | Yes | Yes | Yes | ME - Team | 2026-03-12 | - | - | — | Yes | — | — | — | — | ECR Approval Complete | — | —
ECN/2025/005 | Change in concentricity dimensions of anode disc and jellyroll | Design | 2025 | Approval Done | Drawing change | 0.25 -0.25/+0 mm | 0.25 -0.25/+0.3 mm | As the variation in jellyroll cylindricity is observed to be ~0.3 mm. additional 0.3 mm increase in specification is requested | Assembly -A | ECR | ME Dept | 2025-04-01 | High | No | implemented in line | Approved | Yes | Yes | Yes | Yes | Yes | Yes | ME - Team | 2026-03-12 | - | - | — | Yes | — | — | — | — | ECR Approval Complete | — | —
ECN/2025/006 | Change in weld depth of lid to can welding | Design | 2025 | Approval Done | Drawing change | Weld depth | 0.3 +0.05/-0 mm | 0.3 +0.05/-0.05 mm | Assembly -A | ECR | ME Dept | 2025-04-01 | High | No | implemented in line | Approved | Yes | Yes | Yes | Yes | Yes | Yes | ME - Team | 2026-03-12 | - | - | — | Yes | — | — | — | — | ECR Approval Complete | — | —
Formulas:
Days Remaining = [Target Date]-TODAY()