## Sheet2
ECN/PCN No | ECN Title / Description | Dept | Approval Pending | Change Required | Details of changes required(Before) | Details of changes required(After) | Reason for Change | Affected Area / Equipment | Document Ref | Requested By | Date Raised | Priority | Risk | Feasibility | Status | Approved By ME/Program Head | Approved By Quality Head | Approved By R&D Head | Approved By Plant Head | Approved By Operations/Maintenance Head | Approved by Purchase Head] | Implementation Owner | Target Date | Delay Status | Days Remaining | Actual Closure Date | Validation Required (Y/N) | Validation Status | Monitoring | Monitoring | Monitoring | ECN Status | Open Points | Open Points-Team
ECN/2026/001 | CA - 88 Cathode New Recipe | Process | None | Recipe Change | Conductive carbon % is 1.38 % and binder is 1% | Conductive carbon % is 1.8 % and binder is 0.9% | Reduce resistance + Life cycle Improvement | Cathode Mixing and Calendering | ECR-CA88 | ME Dept | 2026-02-25 | High | Under review | Under review | Raised | — | — | — | — | — | — | ME - Team | 2026-05-31 | On Track | 19 | — | Yes | — | — | — | — | Open | Under review | R&D
ECN/2026/002 | 1.45 g/cc Anode Density electrode | Process | All | Process | Anode Electrode Density-1.58 g/cc | Anode Electrode Density-1.45 g/cc | Life cycle and C rate improvement | Anode Calendering Area | ECR-1.45 g/cc | ME Dept | 2026-02-25 | High | Under review | Under review | Raised | — | — | — | — | — | — | ME - Team | 2026-05-31 | On Track | 19 | — | Yes | — | — | — | — | Open | Risks associated with low peel strength, JR OD rejections and pressure NGs in can insertion discussed along with the action plan addressing these issues. | R&D & ME
ECN/2026/003 | Trim Recycling - Cathode Bottom Trim | Process | Bala/Rajesh | New process Implementation | NA | Powder mixed with % trim loss | Improve the yield and waste by reusing material | Cathode Mixing and Calendering | ECR-Cathode Bottom Trim Loss | ME Dept | 2026-05-11 | High | Contamination | Under review | Raised | No | No | No | No | No | No | ME - Team | 2026-05-31 | On Track | 19 | — | Yes | — | — | — | — | Open | Cells to be used for BESS | ME
ECN/2026/004 | Trim Recycling - Anode Bottom Trim | Process | None | New process Implementation | NA | Powder mixed with % trim loss | Improve the yield and waste by reusing material | Anode Mixing and Calendering | - | ME Dept | 2026-04-06 | High | Contamination | Under review | Upcoming | — | — | — | — | — | — | ME - Team | 2026-05-31 | On Track | FALSE | — | Yes | — | — | — | — | Open | Contamination | ME
ECN/2026/005 | Trim Recycling - Cathode Top Trim | Process | None | New process Implementation | NA | Powder mixed with % trim loss | Improve the yield and waste by reusing material | Cathode Mixing and Calendering | - | ME Dept | 2026-04-06 | High | Contamination | Under review | Upcoming | — | — | — | — | — | — | ME - Team | 2026-05-31 | On Track | FALSE | — | Yes | — | — | — | — | Open | Vendor Trials Done, equipment to be decided based on the results | ME
ECN/2026/006 | Trim Recycling - Anode Top Trim | Process | None | New process Implementation | NA | Powder mixed with % trim loss | Improve the yield and waste by reusing material | Anode Mixing and Calendering | - | ME Dept | 2026-04-06 | High | Contamination | Under review | Upcoming | — | — | — | — | — | — | ME - Team | 2026-05-31 | On Track | FALSE | — | Yes | — | — | — | — | Open | Vendor Trials Done, equipment to be decided based on the results | ME
ECN/2026/007 | Auto Dosing In calendering ( Dosing Tower ) | Process + design | None | Design Change | Manual | Automated | Reduce the spillage of powder and Increase the tool Speed | Cathode + Anode Calendering Area | - | ME Dept | - | - | - | - | Upcoming | — | — | — | — | — | — | ME - Team | — | On Track | - | — | — | — | — | — | — | — | — | ME
ECN/2026/008 | Auto turret In calendering | Process + design | None | Machine Change | Manual | Automated | Reduce the waste of foil + electrode and Setup loss during the start and end of the calendering machine | Cathode + Anode Calendering Area | - | ME Dept | - | - | - | - | Upcoming | — | — | — | — | — | — | ME - Team | — | On Track | - | — | — | — | — | — | — | — | — | ME
ECN/2026/009 | Rev 4 Pin less head - Tab Flattening | Process + design | None | Tool Change |  |  | To improve the process yield | Assembly - A | - | ME Dept | - | - | - | - | Upcoming | — | — | — | — | — | — | ME - Team | — | On Track | - | — | — | — | — | — | — | — | — | No open points
ECN/2026/010 | Automated Core Tube Insertion | Process + design | None | Machine Change | Manual | Automated | To improve the throughput of the process | Assembly -A | - | ME Dept | - | - | - | - | Upcoming | — | — | — | — | — | — | ME - Team | — | On Track | - | — | — | — | — | — | — | — | — | No open points
ECN/2026/011 | EPR Registeration- QR Compliance | Design | Bala | QR Code Change | QR without EPR no. | QR with EPR no. | Include EPR no in the QR for the compliance | Assembly -A | EPR number | ME Dept | 2026-03-14 | High | No risk | Usable | Done | No | Yes | Yes | Yes | Yes | Yes | ME - Team | 2026-03-31 | Delayed | - | — | No | — | — | — | — | validation completed and doc signing off pending | — | No open points
ECN/2026/012 | Anode and Cathode Slitted Foils | Design | Approval Done | Incoming slitted foil-308 mm width in anode and 304 mm in cathode | 340 mm foil width in cathode, 344 mm foil width in anode | 304 mm foil width in cathode, 308 mm foil width in anode | Improve the throughput of the plant by reducing one slitting process | Cathode + Anode Calendering Area | ECR-New Foil | ME Dept | 2026-04-04 | High | No risk | Usable | Done | Yes | Yes | Yes | Yes | Yes | Yes | ME - Team | 2026-03-31 | - | - | — | Yes | — | — | — | — | ECR-Sign off Done | — | No open points
ECN/2026/013 | Formation Protocol Change-SOC Reduction to 30 % instead of 10% | Design | Bala | Protocol Change | 10% SOC reduction | 30% SOC reduction | Increasing the throughput of the plant, as there is no risk with the transportation with 30% SOC | Formation | ECR-SOC Reduction | ME Dept | 2026-04-16 | High | No risk | Usable | Done | No | Yes | Yes | Yes | Yes | Yes | ME - Team | 2026-04-30 | - | - | — | No | — | — | — | — | doc signing off ongoing | — | No open points
ECN/2026/014 | JR OD upper spec revision to 44.55 mm from 44.4 mm | Design | Bala/Rajesh | Specification Change | Upper Spec of Average OD:44.4 mm | Upper Spec of Average OD:44.55 mm | To improve the yield of the winding process and to accomodate the electrodes with the higher thickness within the specifications. | Winding | ECR-JR OD rejections | ME Dept | 2026-05-04 | High | No risk | Usable | Done | No | Yes | Yes | Yes | Yes | Yes | ME - Team | 2026-05-10 | - | - | — | Yes | — | — | — | — | doc signing off ongoing | — | No open points
PCN/2026/001 | Semi Automated UV Curing | Process + design | Bala | Machine Change | Manual | Manual | To improve the throughput of the UV curing process | Assembly -B | PCR-UV Curing | ME Dept | 2026-02-27 | High | No risk | Usable | Done | RnD and QA approved | ME -Team | 2026-03-10 |  | Yes | Completed |  |  |  | validation completed and doc signing off pending |  | Yes | — | — | — | — | ECR-Sign off Ongoing | — | No open points